## Task Breakdown
Task ID | Module / Feature | Sub-Task | Description | Priority | Est. Hours | Phase | Dependencies | Assignee | Status | Notes
T-001 | Project Setup & Infrastructure | Monorepo / Project Scaffolding | Initialise Git repo, folder structure (frontend, backend, shared), .gitignore, linting config | High | 8 | Phase 1 | — | Lead Dev | To Do | Use Turborepo or Nx
T-002 | Project Setup & Infrastructure | CI/CD Pipeline | Configure GitHub Actions pipelines for lint, test, build and deploy | High | 10 | Phase 1 | T-001 | DevOps | To Do | Include staging + prod environments
T-003 | Project Setup & Infrastructure | Docker / Containerisation | Write Dockerfiles for frontend, backend, and database services; docker-compose for local dev | High | 8 | Phase 1 | T-001 | DevOps | To Do
T-004 | Project Setup & Infrastructure | Cloud Environment Setup | Provision cloud resources (AWS/GCP/Azure): VPC, subnets, IAM roles, secrets manager | High | 12 | Phase 1 | T-003 | DevOps | To Do
T-005 | Project Setup & Infrastructure | Database Setup | Create PostgreSQL instance; define initial schemas, migrations tooling (Prisma/Flyway) | High | 8 | Phase 1 | T-004 | Backend Dev | To Do
T-006 | Project Setup & Infrastructure | Environment Configuration | Define env variables for dev/staging/prod; integrate secrets manager | High | 4 | Phase 1 | T-004 | DevOps | To Do
T-007 | Project Setup & Infrastructure | Logging & Monitoring | Integrate structured logging (Winston/Pino) and APM (Datadog/Sentry) | Medium | 6 | Phase 1 | T-004 | DevOps | To Do
T-008 | Authentication & User Management | User Registration API | POST /auth/register — accept email, password, role; hash password; store user record | High | 6 | Phase 1 | T-005 | Backend Dev | To Do | FR-1
T-009 | Authentication & User Management | Email Verification | Generate verification token; send email via SendGrid/SES; GET /auth/verify/:token endpoint | High | 5 | Phase 1 | T-008 | Backend Dev | To Do | FR-2
T-010 | Authentication & User Management | Login & JWT Issuance | POST /auth/login — validate credentials; issue access + refresh JWT tokens | High | 5 | Phase 1 | T-008 | Backend Dev | To Do | FR-3
T-011 | Authentication & User Management | Password Reset Flow | Forgot-password email with secure token; reset-password endpoint with token expiry | High | 5 | Phase 1 | T-010 | Backend Dev | To Do | FR-4
T-012 | Authentication & User Management | Role-Based Access Control | Middleware to enforce Applicant / Recruiter / Admin roles on every protected route | High | 6 | Phase 1 | T-010 | Backend Dev | To Do
T-013 | Authentication & User Management | Registration — Credit Grant | On successful registration award 150 credits to new user via credit service | High | 3 | Phase 1 | T-008 | Backend Dev | To Do | FR-5
T-014 | Authentication & User Management | Registration UI | Sign-up page: role selector, email, password fields, validation, error states | High | 6 | Phase 1 | T-008 | Frontend Dev | To Do
T-015 | Authentication & User Management | Login UI | Login page with JWT storage, redirect on success, error messages | High | 5 | Phase 1 | T-010 | Frontend Dev | To Do
T-016 | Authentication & User Management | Password Reset UI | Forgot-password and reset-password screens | Medium | 4 | Phase 1 | T-011 | Frontend Dev | To Do
T-017 | Authentication & User Management | Auth State Management | Global auth context / Redux slice; persist token; auto-logout on expiry | High | 5 | Phase 1 | T-015 | Frontend Dev | To Do
T-018 | User Profile Management | Applicant Profile API (CRUD) | GET/PUT /applicant/profile — name, phone, skills, experience, education, portfolio links | High | 6 | Phase 2 | T-012 | Backend Dev | To Do
T-019 | User Profile Management | Recruiter Profile API (CRUD) | GET/PUT /recruiter/profile — company name, industry, description, size | High | 5 | Phase 2 | T-012 | Backend Dev | To Do
T-020 | User Profile Management | Applicant Profile UI | Profile editor with skills chips, experience timeline, education cards, portfolio links | High | 8 | Phase 2 | T-018 | Frontend Dev | To Do
T-021 | User Profile Management | Recruiter Profile UI | Company profile editor with logo upload, description, industry dropdown | High | 6 | Phase 2 | T-019 | Frontend Dev | To Do
T-022 | User Profile Management | Profile Completeness Indicator | Calculate & display % completeness; prompt user to fill missing fields | Medium | 4 | Phase 2 | T-020 | Frontend Dev | To Do
T-023 | Resume Upload & Parsing | Resume Upload API | POST /applicant/resume — accept PDF/DOCX; store in S3/cloud storage; return URL | High | 5 | Phase 2 | T-005 | Backend Dev | To Do | FR-6
T-024 | Resume Upload & Parsing | Resume Parsing Integration | Integrate third-party parser (Affinda/Sovren/custom NLP); extract skills, experience, education, contact | High | 10 | Phase 2 | T-023 | Backend Dev | To Do | FR-7
T-025 | Resume Upload & Parsing | Auto-populate Profile from Resume | After parsing, auto-fill applicant profile fields; show diff before saving | High | 6 | Phase 2 | T-024 | Backend Dev | To Do | FR-8
T-026 | Resume Upload & Parsing | Resume Upload UI | Drag-and-drop upload widget, file-type validation, upload progress, parsed-preview modal | High | 7 | Phase 2 | T-023 | Frontend Dev | To Do
T-027 | Job Posting System | Create Job API | POST /jobs — title, company, location, salary, type, skills, description; deduct 10 credits | High | 6 | Phase 2 | T-012 | Backend Dev | To Do | FR-9, FR-10
T-028 | Job Posting System | Edit / Delete Job API | PUT /jobs/:id and DELETE /jobs/:id with ownership guard | High | 4 | Phase 2 | T-027 | Backend Dev | To Do | FR-11
T-029 | Job Posting System | Job Listing — DB Schema & Indexes | Design jobs table; index on location, skills, job_type, salary for fast filtering | High | 4 | Phase 2 | T-005 | Backend Dev | To Do
T-030 | Job Posting System | Create Job UI | Multi-step form: basic info, requirements, description (rich text editor) | High | 8 | Phase 2 | T-027 | Frontend Dev | To Do
T-031 | Job Posting System | Recruiter Job Management UI | My Jobs page: list, status badges, edit/delete actions, view applicants button | High | 7 | Phase 2 | T-028 | Frontend Dev | To Do
T-032 | Job Posting System | Credit Deduction Feedback | Show credit balance before posting; toast/modal warning if balance is low | Medium | 3 | Phase 2 | T-027 | Frontend Dev | To Do
T-033 | Job Search & Discovery | Job Search API | GET /jobs?q=&location=&skills=&type=&salary_min=&salary_max= with pagination | High | 7 | Phase 2 | T-029 | Backend Dev | To Do | FR-12, FR-13
T-034 | Job Search & Discovery | Full-Text Search Integration | Implement Postgres full-text search or Elasticsearch index on title and description | High | 8 | Phase 2 | T-033 | Backend Dev | To Do
T-035 | Job Search & Discovery | Job Search UI — Filters Panel | Sidebar filters: location, experience, salary slider, skills tags, job type checkboxes | High | 8 | Phase 3 | T-033 | Frontend Dev | To Do
T-036 | Job Search & Discovery | Job Card & Detail Page | Job card component; full job detail page with apply button, company info, share link | High | 7 | Phase 3 | T-035 | Frontend Dev | To Do
T-037 | Job Search & Discovery | Saved / Bookmarked Jobs | POST /applicant/saved-jobs/:id; UI save button; saved jobs list page | Medium | 4 | Phase 3 | T-033 | Backend Dev + Frontend Dev | To Do
T-038 | Job Application System | Submit Application API | POST /applications — link applicant + job; store cover letter / resume snapshot | High | 5 | Phase 3 | T-027 | Backend Dev | To Do | FR-14
T-039 | Job Application System | Recruiter: View Applications API | GET /jobs/:id/applications — paginated list with applicant snapshot | High | 5 | Phase 3 | T-038 | Backend Dev | To Do | FR-15
T-040 | Job Application System | Recruiter: Update Application Status API | PATCH /applications/:id/status — shortlisted, rejected, in-review, hired | High | 4 | Phase 3 | T-039 | Backend Dev | To Do | FR-16
T-041 | Job Application System | Applicant: Application Tracking API | GET /applicant/applications — list with status history | High | 4 | Phase 3 | T-038 | Backend Dev | To Do | FR-18
T-042 | Job Application System | Apply Flow UI | Apply modal: review resume, write cover letter, submit; duplicate-application guard | High | 7 | Phase 3 | T-038 | Frontend Dev | To Do
T-043 | Job Application System | Recruiter Candidate Review UI | Kanban / table view of applicants; expandable profile drawer; status update dropdown | High | 10 | Phase 3 | T-040 | Frontend Dev | To Do
T-044 | Job Application System | Applicant Application Tracker UI | Timeline view of all applications with status badges and recruiter name | High | 6 | Phase 3 | T-041 | Frontend Dev | To Do
T-045 | Messaging System | Message DB Schema | conversations and messages tables; indexes on participant IDs and created_at | High | 4 | Phase 3 | T-005 | Backend Dev | To Do
T-046 | Messaging System | Send / Receive Message API | POST /messages; GET /conversations/:id/messages with pagination | High | 6 | Phase 3 | T-045 | Backend Dev | To Do | FR-19, FR-20
T-047 | Messaging System | Real-Time Messaging (WebSocket / SSE) | Integrate Socket.io or SSE for live message delivery | High | 8 | Phase 3 | T-046 | Backend Dev | To Do
T-048 | Messaging System | Message Notification Trigger | Trigger in-app + email notification when new message arrives | Medium | 4 | Phase 3 | T-047 | Backend Dev | To Do | FR-21
T-049 | Messaging System | Messaging UI | Conversation list sidebar + chat window; unread badge; message timestamps | High | 10 | Phase 3 | T-047 | Frontend Dev | To Do
T-050 | Referral Module | Generate Referral Code API | Auto-generate unique referral code on registration; store in users table | High | 3 | Phase 2 | T-008 | Backend Dev | To Do | FR-22
T-051 | Referral Module | Referral Link Tracking | GET /ref/:code — record referral visit; attach referrer to new registration | High | 4 | Phase 2 | T-050 | Backend Dev | To Do | FR-23
T-052 | Referral Module | Referral Reward Logic | On referral signup, credit referrer + referral with configured reward amounts | High | 5 | Phase 2 | T-051 | Backend Dev | To Do | FR-24
T-053 | Referral Module | Referral Dashboard UI | Show referral link/code, copy button, referred users list, total credits earned | Medium | 5 | Phase 3 | T-052 | Frontend Dev | To Do
T-054 | Credit System | Credit Ledger DB Schema | credit_transactions table: user_id, type, amount, balance_after, description, created_at | High | 4 | Phase 1 | T-005 | Backend Dev | To Do
T-055 | Credit System | Credit Service (Internal) | Service layer: debit(), credit(), getBalance(); atomic transactions to prevent race conditions | High | 6 | Phase 1 | T-054 | Backend Dev | To Do | FR-25, FR-26
T-056 | Credit System | Credit Balance API | GET /credits/balance and GET /credits/history (paginated) | High | 3 | Phase 2 | T-055 | Backend Dev | To Do
T-057 | Credit System | Credit Wallet UI | Header balance widget; credit history table with transaction type, amount, date | Medium | 5 | Phase 2 | T-056 | Frontend Dev | To Do
T-058 | Subscription & Payments | Subscription Plan Config | Define plans in DB/config: name, credit amount, price; seed initial plans | High | 3 | Phase 2 | T-005 | Backend Dev | To Do
T-059 | Subscription & Payments | Payment Gateway Integration | Integrate Stripe/Razorpay: create checkout session, handle webhooks for success/failure | High | 10 | Phase 2 | T-058 | Backend Dev | To Do | FR-27
T-060 | Subscription & Payments | Credit Top-Up on Payment | Webhook handler: verify payment, credit user account, record transaction | High | 5 | Phase 2 | T-059 | Backend Dev | To Do | FR-28
T-061 | Subscription & Payments | Subscription Plans UI | Pricing page with plan cards; checkout redirect; success/failure pages | High | 7 | Phase 2 | T-059 | Frontend Dev | To Do
T-062 | Subscription & Payments | Payment History UI | List of past purchases with invoice download links | Medium | 4 | Phase 3 | T-060 | Frontend Dev | To Do
T-063 | Notifications System | Notification DB Schema | notifications table: user_id, type, message, read, created_at | High | 3 | Phase 2 | T-005 | Backend Dev | To Do
T-064 | Notifications System | Notification Service | Internal service: createNotification(); dispatches email + in-app events | High | 5 | Phase 2 | T-063 | Backend Dev | To Do | FR-29
T-065 | Notifications System | Email Notification Templates | Design transactional email templates (job match, application update, message, referral) | Medium | 6 | Phase 2 | T-064 | Backend Dev + Designer | To Do | Use SendGrid/SES
T-066 | Notifications System | In-App Notification Bell UI | Bell icon with unread count; dropdown list; mark-all-read; notification detail link | Medium | 5 | Phase 3 | T-064 | Frontend Dev | To Do
T-067 | Notifications System | Real-Time Notification Push | Push new notifications to client via WebSocket / SSE without page refresh | Medium | 5 | Phase 3 | T-066 | Backend Dev | To Do
T-068 | AI Job Matching | Skill Extraction & Normalisation | Normalise raw skills from profiles and jobs to canonical taxonomy (O*NET / custom) | High | 8 | Phase 3 | T-024 | ML Engineer | To Do | FR-30
T-069 | AI Job Matching | Matching Algorithm | TF-IDF or embedding-based (sentence-transformers) cosine similarity between candidate and job | High | 12 | Phase 3 | T-068 | ML Engineer | To Do
T-070 | AI Job Matching | Recommendation API | GET /applicant/recommendations — return top-N matched jobs with score | High | 5 | Phase 3 | T-069 | Backend Dev | To Do | FR-31
T-071 | AI Job Matching | Recommendations UI | Dashboard widget + full recommendations page with match-score badges | High | 6 | Phase 4 | T-070 | Frontend Dev | To Do
T-072 | AI Job Matching | Model Retraining Pipeline | Batch job to retrain/refresh embeddings nightly using new profiles and job data | Medium | 8 | Phase 4 | T-069 | ML Engineer | To Do
T-073 | Analytics Dashboard | Analytics Data Collection | Track job views, application events, profile views in analytics_events table | Medium | 5 | Phase 3 | T-038 | Backend Dev | To Do
T-074 | Analytics Dashboard | Recruiter Analytics API | GET /recruiter/analytics — applications count, job views, funnel stages, candidate quality | Medium | 6 | Phase 4 | T-073 | Backend Dev | To Do
T-075 | Analytics Dashboard | Recruiter Analytics UI | Charts (bar, funnel, line) for job performance; date-range filter; exportable CSV | Medium | 8 | Phase 4 | T-074 | Frontend Dev | To Do | Use Recharts/Chart.js
T-076 | Admin Dashboard | Admin Auth & Guard | Admin-only JWT role check; separate admin login if required; audit log | High | 4 | Phase 3 | T-012 | Backend Dev | To Do
T-077 | Admin Dashboard | User Management API | GET /admin/users; PATCH /admin/users/:id/status (ban/unban); DELETE user | High | 5 | Phase 3 | T-076 | Backend Dev | To Do
T-078 | Admin Dashboard | Job Moderation API | GET /admin/jobs?status=pending; PATCH /admin/jobs/:id/approve¦reject | High | 5 | Phase 3 | T-076 | Backend Dev | To Do
T-079 | Admin Dashboard | Credit Management API | GET /admin/credits; manual credit adjustment endpoint with reason | Medium | 4 | Phase 3 | T-076 | Backend Dev | To Do
T-080 | Admin Dashboard | Platform Metrics API | GET /admin/metrics — DAU, new registrations, jobs posted, revenue | Medium | 5 | Phase 4 | T-076 | Backend Dev | To Do
T-081 | Admin Dashboard | Admin UI — Users & Jobs | Data tables with search/filter; action menus; confirmation dialogs | High | 10 | Phase 4 | T-077 | Frontend Dev | To Do
T-082 | Admin Dashboard | Admin UI — Metrics Overview | KPI cards and charts: user growth, job activity, credit usage, revenue | Medium | 7 | Phase 4 | T-080 | Frontend Dev | To Do
T-083 | Testing & QA | Unit Tests — Backend | Jest/Vitest unit tests for all service functions; aim for 80% coverage | High | 16 | Phase 2+ | T-010 | QA / Dev | To Do
T-084 | Testing & QA | Integration Tests — API | Supertest API integration tests for all endpoints with test DB | High | 14 | Phase 3+ | T-083 | QA / Dev | To Do
T-085 | Testing & QA | Unit & Component Tests — Frontend | React Testing Library tests for key components; mock API calls | Medium | 12 | Phase 3+ | T-014 | QA / Frontend Dev | To Do
T-086 | Testing & QA | E2E Tests | Playwright/Cypress E2E flows: register, post job, apply, messaging, payment | High | 14 | Phase 4 | T-084 | QA | To Do
T-087 | Testing & QA | Performance Testing | k6 load tests for 10k concurrent users on critical endpoints | Medium | 8 | Phase 4 | T-086 | QA / DevOps | To Do | NFR-4.1
T-088 | Testing & QA | Security Audit | OWASP Top 10 review; pen-test auth flows, payment, RBAC; fix findings | High | 10 | Phase 4 | T-086 | Security / Dev | To Do | NFR-4.2
T-089 | Deployment & DevOps | Staging Environment | Deploy full stack to staging; smoke tests; share staging URL with stakeholders | High | 6 | Phase 3 | T-003 | DevOps | To Do
T-090 | Deployment & DevOps | Production Environment | Production infra: auto-scaling groups, RDS Multi-AZ, CDN for assets | High | 10 | Phase 4 | T-089 | DevOps | To Do | NFR-4.3
T-091 | Deployment & DevOps | Database Backup & Recovery | Automated daily DB snapshots; test restore procedure; document RTO/RPO | High | 5 | Phase 4 | T-090 | DevOps | To Do | NFR-4.4
T-092 | Deployment & DevOps | SSL / TLS & Domain Setup | Configure custom domain, HTTPS certificates (ACM), HSTS headers | High | 3 | Phase 4 | T-090 | DevOps | To Do
T-093 | Deployment & DevOps | Production Go-Live Checklist | Final smoke tests, enable monitoring alerts, update status page, announce launch | High | 4 | Phase 4 | T-092 | All Leads | To Do

## Summary
Module | Tasks | Est. Hours
AI Job Matching | 5 | 39
Admin Dashboard | 7 | 40
Analytics Dashboard | 3 | 19
Authentication & User Management | 10 | 50
Credit System | 4 | 18
Deployment & DevOps | 5 | 28
Job Application System | 7 | 41
Job Posting System | 6 | 32
Job Search & Discovery | 5 | 34
Messaging System | 5 | 32
Notifications System | 5 | 24
Project Setup & Infrastructure | 7 | 56
Referral Module | 4 | 17
Resume Upload & Parsing | 4 | 28
Subscription & Payments | 5 | 29
Testing & QA | 6 | 74
User Profile Management | 5 | 29
TOTAL | 93 | 590
Phase Breakdown |  |  | Priority Breakdown
Phase | Est. Hours |  | Priority | Count
Phase 1 | 116 |  | High | 72
Phase 2 | 163 |  | Medium | 21
Phase 2+ | 16
Phase 3 | 165
Phase 3+ | 26
Phase 4 | 104